## Working route
Blackboard Group No 03 Class ZBB | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-07-27 | Wednesday Jul.26 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | -224 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files | 2 hours | Friday Jul.28 | DONE | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Saturday Jul.29 | DONE | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Wednesday Aug.2 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.14 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Monday Dec.12 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.12 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." | 1 hour | Sunday Jul.30 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Wednesday Aug.2 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Aug.7 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Dec.12 | TO DO
Gerry Iglesias Fundamentals | Analyze and review the "fundamentals" module with the given source code file. Review the document "Programming Comments.pdf" for reference. | Share with the team the "fundamentals-review.docx" document containing a summary of the "fundamentals" module by uploading to MS Teams channel. | 1.5 hours | Saturday Jul.29 | DONE | Develop program version 1 of the "fundamentals" module, including the ".h" and ".c" files. Prepare a set of unit test cases in the "fundamentals-test-cases.xlsx", along with post-test results. Capture test case inputs and outputs as text in the "fundamentals-testing.txt". Upload the files to MS Teams channel in the root of Files. | Share the bug free source codes .h and .c file of "fundamentals" module in the MS Teams Channel. Share the filled up Excel file "fundamental-test-cases.xlsx" in the MS Teams Channel. Share the filled up text files "fundamental-testing.txt" in the MS Teams Channel. | 5 hours | Thursday Aug.3 | TO DO | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Aug.8 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
Rafi Islam Arnob Manipulations | Analyze and review the "manipulations" module with the given source code file. Review the document "Programming Comments.pdf" for reference. | Share with the team the "manipulations-review.docx" containing a summary of the "manipulations" module by uploading to MS Teams channel. | 2.5 hours | Saturday Jul.29 | DONE | Develop program version 1 of the "manipulations" module, including the ".h" and ".c" files. Prepare a set of unit test cases in the "manipulations-test-cases.xlsx", along with post-test results. Capture test case inputs and outputs as text in the "manipulations-testing.txt". Upload the files to MS Teams channel in the root of Files. | Share the bug free source codes .h and .c file of "manipulations" module in the MS Teams Channel. Share the filled up Excel file "manipulations-test-cases.xlsx" in the MS Teams Channel. Share the filled up text file "manipulations-testing.txt" in the MS Teams Channel. | 5 hours | Thursday Aug.3 | TO DO | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Aug.8 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
Tareq Ahmed Tokenizing | Analyze and review the "tokenizing" module with the given source code file. Review the document "Programming Comments.pdf" for reference. | Share with the team the "tokenizing-review.docx" document containing a summary of the "tokenizing" module by uploading to MS Teams channel. | 1.5 hours | Saturday Jul.29 | DONE | Develop program version 1 of the "tokenizing" module, including the ".h" and ".c" files. Prepare a set of unit test cases in the "tokenizing-test-cases.xlsx", along with post-test results. Capture test case inputs and outputs as text in the "tokenizing-testing.txt". Upload the files to MS Teams channel in the root of Files. | Share the bug free source codes .h and .c file of "tokenizing" module in the MS Teams Channel. Share the filled up Excel file "tokenizing-test-cases.xlsx" in the MS Teams Channel. Share the filled up text file "tokenizing-testing.txt" in the MS Teams Channel. | 5 hours | Thursday Aug.3 | TO DO | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Aug.8 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Tuesday Dec.13 |  |  |  |  | Tuesday Dec.13
Harold Talavera Conversions Team Leader | Identify the specific tasks of each team member and then compile their inputs once they are provided. Include and document the necessary details in the project plan Excel file. Analyze and review the "conversions" module with the given source code file. Review the document "Programming Comments.pdf" for reference. | Share with the team the Final-Project-Plan.xlsx project plan document. Share with the team the "conversions-review.docx" document containing a summary of the "conversions" module by uploading to MS Teams channel. | 2.5 hours | Sunday Jul.30 | DONE | Develop program version 1 of the "converting.c", and merge c files to "main.c" file. Prepare a set of unit test cases in the "converting-test-cases.xlsx" and "Final-Project-Test-Cases.xlsx", along with post-test results. Capture test case inputs and outputs as text in the "converting.txt" and "main-testing.txt". Assembles files into the root of a ZIP archive named Final-Project-Bb03.zip | Share the bug free source codes .h and .c file of "conversions" and "main" module in the MS Teams Channel. Share the filled up Excel files "conversions-test-cases.xlsx" and "Final-Project-Test-Cases.xlsx" in the MS Teams Channel. Share the filled up text files "conversions-testing.txt" and "main-testing.txt" in the MS Teams Channel. Share and upload the Final-Project-Bb03.zip. | 5 hours | Friday Aug.4 | TO DO | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Wednesday Aug.9 |  | REPLACE THIS with your action items and work breakdown structure for this Version |  |  | Wednesday Dec.14 |  |  |  |  | Wednesday Dec.14
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.